## Slide 1: TONAL SCIENCE
Topic 1: 3D Motion Capture from 2D Videos
Deepa Sharanya S
Albert Joseph A
Avinash S
Priyadarshini P

## Slide 2: Overall Plan
Our topic is “Capturing Human motion from real-time 2D videos using OpenPose and Mediapipe model in any of the free and open source 3D computer graphics toolset”. We planned to add plugin available in the computer graphics toolset to make the motion capture along with Openpose and MediaPipe to capture the motion better. Then we create a 3D human model using 3D computer graphics technology software. Then Transfer the captured motion to the model in the open source 3D computer graphics toolset. Create pose variations in the model using python script and show the variations in the pose. We planned to capture complex motions using mediapipe.

## Slide 3: Detailed Schedule
# | Task | Owner | Start Date | End Date | Dependencies
1 | Creation of 3D model | Avinash S | 02.10.2021 | 04.10.2021 | Mixamo
2 | Integrating Openpose and Blender to capture motion from a real-time video | Albert Joseph A | 04.10.2021 | 08.10.2021 | OpenPose model, Blender
3 | Integrating Mediapipe’s Pose and Blender to caputer motion automatically in realtime videos | Priyadarshini P | 04.10.2021 | 08.10.2021 | Mediapipe model, Blender
4 | Transferring the captured motion to a 3D avatar as animation. | Deepa Sharanya S | 08.10.2021 | 10.10.2021 | Blender, Json
5 | Creation of pose variations from 3D avatars using Python Script | Avinash S | 10.10.2021 | 12.10.2021 | Blender, Python
6 | Model testing and debugging | Albert Joseph A | 12.10.2021 | 12.10.2021 | Blender
7 | Uploading finished project in Git Repo | Deepa Sharanya S | 13.10.2021 | 13.10.2021 | GitHub, Blender

## Slide 4: Risks & Mitigation / Action plan
# | Risk | Severity | Probability | Mitigation / Action Plan
1 | Frame rate drop | Gives rise to latency in FPS | 20% | Identifying plugins to overcome
2 | MoCap is quite difficult while using OpenPose and MediaPipe | Implementation of model may take much time | 80% | Using native plug-ins